## 1. Exec Summary
SHEET 1 — EXECUTIVE SUMMARY
RKM Foundation launch readiness. Evidence-based, verified 14 Jun 2026. Pre-launch (Razorpay TEST mode).
Dimension | Score / Verdict | Basis (evidence)
Overall Readiness | 7.5 / 10 | Engineering complete & sound; blocked only by operational steps.
Frontend Readiness | 9 / 10 | All pages live & rendering on vercel.app; donate widget, forms, legal pages work.
Backend Readiness | 9 / 10 | Ledger, webhook-as-source-of-truth, gapless receipt numbering, audit trail DB-enforced.
Automation Readiness | 7 / 10 | All donor + form emails built & wired; receipt PDF generates; card->webhook->inbox unverified.
Security Readiness | 7.5 / 10 | Admin 401 verified, webhook HMAC verified, rate-limit present, secrets server-side. Shared secrets need rotation.
Compliance Readiness | 9 / 10 | 12A/80G/CSR-1/DARPAN/PAN consistent; provisional + Form 10BE wording correct; immutable ledger.
Donation Readiness | 5 / 10 | Pipeline complete but TEST mode; cannot take real money until live keys + verified test donation.
GO / NO-GO | NO-GO today | Reasons are operational, not engineering.
Launch Blocker 1 | Razorpay in TEST mode | No live keys; cannot process real money.
Launch Blocker 2 | Donor receipt + ack emails unverified end-to-end | Components proven independently; no real test donation has confirmed inbox delivery.
Launch Blocker 3 | DNS not cut over | Site serves on vercel.app only; rkmfoundation.com not pointed yet.
Founder Action 1 | Add live Razorpay keys + webhook secret | In Vercel env, then redeploy.
Founder Action 2 | Run one test-card donation | Confirm both emails + PDF receipt arrive.
Founder Action 3 | Cut over DNS | A + CNAME at registrar.
Founder Action 4 | Rotate secrets shared in chat | Supabase service key, Resend, admin token, webhook secret.
Founder Action 5 | Reset demo/test data | On founder 'go'.
Estimated hours to launch | ~2-3 hours | 45m rotation, 30m live keys, 30m test+verify, 15m DNS, 15m demo reset.

## 2. Software
SHEET 2 — SOFTWARE INVENTORY
Every service and dependency used by the project, with access points.
Software | Purpose | Environment | Login URL | Admin URL | Owner | Criticality | Founder Access | Status
Vercel | Hosting, serverless APIs, build/deploy, SSL | Production | vercel.com/login | vercel.com/dashboard | Founder | Critical | Verified | Live (*.vercel.app)
Supabase | Postgres DB, storage, service keys | Production | supabase.com/dashboard/sign-in | dashboard/project/rnwifjrdhdhemrlmgjij | Founder | Critical | Verified | Live, healthy
Razorpay | Payment gateway (orders, subs, webhooks) | TEST mode | dashboard.razorpay.com | dashboard.razorpay.com > Settings | Founder | Critical | Verify | Test keys active; live needed
Resend | Transactional email (donor/form/receipt) | Production | resend.com/login | resend.com > API Keys/Domains | Founder | Critical | Verified | Live; rkm.support verified
Domain Registrar | Owns rkmfoundation.com | Production | (registrar of record) | registrar DNS panel | Founder | Critical | Verify | Owned; DNS not pointed
DNS Provider | Routes domain -> Vercel | Production | (registrar/DNS panel) | DNS records panel | Founder | Critical | Verify | Not cut over
Supabase Storage | Private 'receipts' bucket (PDFs) | Production | (same as Supabase) | Supabase > Storage | Founder | High | Verified | Live
Email domain rkm.support | Verified sender for all mail | Production | (Resend/DNS) | Resend > Domains | Founder | Critical | Verified | Verified
Analytics | Traffic/visitor analytics | - | - | - | Founder | Low | n/a | Not installed (none in code)
Monitoring | Uptime/error alerting | - | - | - | Founder | Medium | n/a | Not installed (Vercel logs only)
pdf-lib (library) | Generates 80G receipt PDF | Bundled | n/a | n/a | n/a | High | n/a | Working
resend SDK (library) | Resend API client | Bundled | n/a | n/a | n/a | High | n/a | Working
Next.js / React / Tailwind | App framework + UI | Bundled | n/a | n/a | n/a | Critical | n/a | Working
Hidden dep: Resend domain verify | All email fails silently if it lapses | Production | resend.com | Resend > Domains | Founder | Critical | Verified | Monitor
Hidden dep: receipts bucket | Receipt PDFs depend on it | Production | supabase.com | Supabase > Storage | Founder | High | Verified | Monitor
Hidden dep: webhook secret match | Mismatch -> all webhooks 401 | Production | both Razorpay+Vercel | both panels | Founder | Critical | Verified | Keep in sync

## 3. Credentials
SHEET 3 — ACCESS & CREDENTIAL REGISTER
All keys/secrets/tokens. Anything pasted in chat is treated as exposed. No secret is hardcoded in source or printed in logs.
System | Credential Name | Purpose | Access Level | Stored Where | Founder Access | Rotate? | Risk Level
Supabase | SUPABASE_SERVICE_KEY | Full DB read/write (bypasses RLS) | Highest (god-mode) | Vercel env | Yes | MUST ROTATE BEFORE LAUNCH | Critical (in chat)
Supabase | SUPABASE_URL | DB endpoint | Public-ish | Vercel env | Yes | SAFE | Low
Razorpay | RAZORPAY_KEY_ID / KEY_SECRET (test) | Test gateway auth | High (test only) | Vercel env | Yes | SHOULD ROTATE (replaced by live) | Medium (in chat)
Razorpay | NEXT_PUBLIC_RAZORPAY_KEY_ID | Client checkout key id | Public by design | Vercel env / client | Yes | SAFE | Low
Razorpay | RAZORPAY_WEBHOOK_SECRET | Verify webhook authenticity | High | Vercel env | Yes | MUST ROTATE BEFORE LAUNCH | Critical (in chat)
Resend | RESEND_API_KEY | Send all transactional email | High | Vercel env | Yes | MUST ROTATE BEFORE LAUNCH | High (in chat)
Admin Portal | ADMIN_ACCESS_TOKEN | Gate /admin + admin APIs | High (PII access) | Vercel env | Yes | MUST ROTATE BEFORE LAUNCH | High (in chat)
Email | FORMS_FROM_EMAIL / FORMS_TO_EMAIL | Sender/recipient addresses | Config | Vercel env | Yes | SAFE | Low
Email | RECEIPTS_FROM_EMAIL | Optional receipt sender override | Config | Vercel env (optional) | Yes | SAFE | Low
DB | DEFAULT_FUND_ID | Default fund for webhook donations | Config | Vercel env (optional) | Yes | SAFE | Low
JWT Secrets | (none custom) | No custom JWT secret in app code | n/a | n/a | n/a | SAFE | Low
Exposure review (where credentials appeared)
Chat | Supabase key, Resend key, admin token, webhook secret, Razorpay test keys | Pasted in earlier session | - | Chat history | - | MUST ROTATE BEFORE LAUNCH | Critical
Source Code | None | All secrets via process.env; none hardcoded | - | Verified in lib/email.ts, lib/db.ts, webhook route | - | SAFE | Low
Logs | None | Logs print event types/receipt nos only | - | Verified runtime logs | - | SAFE | Low
Screenshots / Docs | None secret | No secret values captured | - | - | - | SAFE | Low

## 4. Rotation Plan
SHEET 4 — SECRET ROTATION PLAN
Rotate everything exposed with near-zero downtime. Vercel keeps every prior deployment -> Instant Rollback available throughout.
Order | Secret | Risk | Rotation Required | Priority | Downtime Risk | Rollback Available | Exact Steps | Est. Time
1 | SUPABASE_SERVICE_KEY | Full DB compromise (donor PII) | Yes - before launch | P0 | Low (brief on redeploy) | Yes (Instant Rollback) | Supabase > Settings > API > reset service_role > update Vercel env > Redeploy | ~10 min
2 | ADMIN_ACCESS_TOKEN | Unauthorized PII / export access | Yes - before launch | P0 | None (admin login only) | Yes | New strong random string > update Vercel env > Redeploy (old sessions invalid) | ~5 min
3 | RESEND_API_KEY | Spoofed email from your domain | Yes - before launch | P0 | Low (email pauses till deploy) | Yes | Resend > API Keys > create new > delete old > update Vercel > Redeploy | ~5 min
4 | RAZORPAY_WEBHOOK_SECRET | Forged webhook events | Yes - at launch w/ live keys | P0 | Low (set in Razorpay+Vercel together) | Yes | Razorpay > Webhooks > set endpoint+new secret > update Vercel > Redeploy | ~10 min
5 | RAZORPAY test keys | Test env only | Replaced by live keys | P0 | n/a (test->live switch) | Yes | Razorpay > Live > generate live keys > update 3 Vercel vars > Redeploy | ~15 min
| TOTAL | - | - | - | - | - | Rollback: Vercel 'Instant Rollback' restores prior deploy + env snapshot if a new key breaks anything | ~35-45 min

## 5. Env Variables
SHEET 5 — ENVIRONMENT VARIABLES
All env vars with required/optional, current set state (by evidence), and production dependency.
Variable | Purpose | Required | Currently Set | Production Dependency | Class | Risk
SUPABASE_URL | DB endpoint | Yes (code default) | Yes (writes work) | All DB ops | Production | Low
SUPABASE_SERVICE_KEY | Service-role DB auth | Yes | Yes (writes succeed) | All DB ops | Production | Critical
RAZORPAY_KEY_ID | Gateway auth (server) | Yes | Yes (test) | Order/sub creation | Test (switch to live) | High
RAZORPAY_KEY_SECRET | Gateway auth (server) | Yes | Yes (test) | Order/sub creation | Test (switch to live) | Critical
NEXT_PUBLIC_RAZORPAY_KEY_ID | Checkout (client) | Yes | Yes (test) | Checkout widget | Test (switch to live) | Public by design
RAZORPAY_WEBHOOK_SECRET | Webhook HMAC verify | Yes | Yes (sig verifies; bad->401) | Payment capture pipeline | Test (switch to live) | Critical
RESEND_API_KEY | Email send | Yes | Yes (form emails send, no '(not configured)' log) | All outbound email | Production | High
FORMS_TO_EMAIL | Admin notification recipient | No (default info@rkm.support) | Yes | Form admin notifications | Production | Low
FORMS_FROM_EMAIL | Verified sender address | Recommended | Yes (website@rkm.support) | All outbound email | Production | Low
RECEIPTS_FROM_EMAIL | Optional receipt sender override | No | Optional (falls back) | Receipt email 'from' | Optional | Low
DEFAULT_FUND_ID | Fund for webhook donations | No | Optional (falls back to 'General Fund') | Sub/webhook donations | Optional | Low
ADMIN_ACCESS_TOKEN | Admin gate | Yes | Yes (APIs 401 without it) | /admin + admin APIs | Production | High
Missing variables (required, confirmed missing) | None - all required vars evidenced as set in TEST config | - | - | - | - | Low
SSL | Auto-issued by Vercel; will auto-issue for rkmfoundation.com after DNS cutover | - | Auto | TLS | Production | Low

## 6. Automation
SHEET 6 — AUTOMATION MATRIX
Every workflow with trigger, status, test state, evidence and failure handling. Classify: Working / Built but Unverified / Missing.
Workflow | Trigger | Status | Tested | Evidence | Failure Handling | Owner
Donation order creation | POST /api/donate | Working | Yes | Live checkout opens; 2 'initiated' rows | 400/500 JSON; rate-limited | System
Webhook - payment capture | Razorpay payment.captured | Working | Partial | 2 payment_event rows; bad-sig 401 verified | 500 -> Razorpay retries | System
Webhook idempotency | Duplicate event id | Working | Yes | UNIQUE(provider_event_id); duplicate->early return | Constraint-enforced | System
Receipt generation + numbering | issueReceipt() idempotent | Working | Yes | 3 receipts; allocate_receipt_no RPC; UNIQUE(receipt_no); 0 dupes | Idempotent via receipt_id | System
Receipt PDF | receiptPdfBytes() pdf-lib | Working | Yes | Valid %PDF- file generated (sample) | Throws -> caught by caller | System
Donation email (acknowledgement) | Webhook -> sendDonationEmails ('Thank You for Helping an Animal Today') | Built but Unverified | No | Code wired; Resend path proven via forms; not confirmed in real inbox | try/catch; never breaks webhook 200 | System
80G receipt email (PDF attached) | Same path ('Your Donation Receipt - RKM Foundation') | Built but Unverified | No | Code+PDF+attachment wired; needs live test | try/catch; non-blocking | System
Thank-you email (donor ack) | Same as donation email above | Built but Unverified | No | Same path | try/catch | System
Newsletter welcome | POST /api/forms (newsletter) -> sendNewsletterWelcome | Working | Partial | Same proven Resend path | try/catch; logged '[forms] ack' | System
Contact acknowledgement | /api/forms (contact) -> sendFormAck | Working | Yes | Live submit -> POST /api/forms 200, no error log | try/catch; non-blocking | System
CSR acknowledgement | /api/forms (csr) -> sendFormAck | Working | Partial | Same code path as contact (proven) | try/catch | System
Partner acknowledgement | /api/forms (partner) -> sendFormAck | Working | Partial | Same code path (proven) | try/catch | System
Careers acknowledgement | /api/forms (careers) -> sendFormAck | Working | Partial | Same code path (proven) | try/catch | System
Fundraiser acknowledgement | /api/forms (fundraiser-create) -> sendFormAck | Working | Partial | Same code path (proven) | try/catch | System
Admin form notification | /api/forms -> sendFormEmail -> FORMS_TO_EMAIL | Working | Yes | Live submit produced admin email, no error | throws on Resend error | System
Admin export | /admin (token-gated) | Working | Partial | Admin gate 401 without token; export UI present | Server-enforced gate | Founder
Audit trail generation | DB-side on ledger writes | Working | Yes | 33 audit_trail rows | DB triggers | System
Compliance events | completeCompliance() on PAN capture | Working | Partial | 1 compliance_event row recorded | try/catch | System
Donor nurture / monthly impact / 10BE auto-issue | - | Missing | No | Roadmap (M5/M6); not launch-critical | n/a | Founder

## 7. Data Integrity
SHEET 7 — DATABASE & DATA INTEGRITY
Queried live 14 Jun 2026. Integrity is schema-enforced (UNIQUE + FK), not merely currently clean.
Table | Records | Orphans | Duplicates | Constraints | Status
donation | 13 (10 paid, 2 initiated, 1 failed) | 0 | 0 dup payment_ref | FK -> donor/fund/receipt/subscription; UNIQUE(payment_ref) | Clean
donor | 13 | 0 | - | PK donor_id; self-ref FK | Clean
receipt | 3 | 0 (all link to a donation) | 0 dup receipt_no | UNIQUE(receipt_no); FK -> donation; FK supersedes | Clean
payment_event | 2 | - | - | UNIQUE(provider_event_id) [idempotency]; FK -> donation | Clean
subscription | 1 | - | - | FK from donation | Clean
audit_trail | 33 | - | - | Append-only ledger | Clean
compliance_event | 1 | - | - | FK -> donation | Clean
Note: paid donations without receipt | 7 | Expected - historical test rows predate auto-receipt wiring; clear on demo reset | - | Not a defect; webhook now issues a receipt on every payment.captured | OK

## 8. Security
SHEET 8 — SECURITY AUDIT
Severity-ranked. No Critical open items in code; the highest items are secret rotation and a shared static admin token.
Risk ID | Risk | Severity | Evidence | Impact | Mitigation | Status
SEC-01 | Live secrets shared in chat | Major | Supabase/Resend/admin/webhook keys pasted earlier | Compromise if chat leaks | Rotate all before launch (Sheet 4) | Open - founder action
SEC-02 | Admin auth is single shared static token | Medium | ADMIN_ACCESS_TOKEN gate; no MFA/per-user/lockout | Token guess/leak -> PII access | Rotate + rate-limit token check; add Supabase Auth (M4) | Open
SEC-03 | Admin interim-access note exposed | Medium | /admin shows 'Supabase Auth roles arrive in M4' | Info disclosure | Remove note | Open (minor)
SEC-04 | Donor-email enumeration via /api/compliance | Medium | Distinct 'not found' vs success on PAN form | Confirm donor existence | Uniform response + rate-limit | Open
SEC-05 | Admin access / authentication | Low (controlled) | Admin APIs return 401 without token (verified live) | - | Server-enforced gate working | Pass
SEC-06 | Rate limiting | Low (controlled) | throttle() on /api/donate and /api/forms (429) | Abuse/spam | Present; honeypot + min-fill-time on forms | Pass
SEC-07 | Webhook validation | Low (controlled) | HMAC verify; bad signature -> 401 (verified) | Forged events blocked | verifyWebhookSignature enforced | Pass
SEC-08 | Secret exposure in code/logs | Low | No hardcoded secrets; logs print no secrets (verified) | - | All via process.env | Pass
SEC-09 | API security / public exposure | Low | Admin APIs gated; donate/forms validated+throttled | - | Input validation via guard.ts | Pass
SEC-10 | PII exposure | Low (controlled) | Donor PAN behind service-role + admin token; maskPan on display | - | Access-controlled | Pass
SEC-11 | Logging hygiene | Low | Error logs are generic ('[webhook] persist error') | - | No PII/secret in logs | Pass

## 9. Compliance
SHEET 9 — COMPLIANCE AUDIT
Indian charitable-trust compliance. All registrations present and consistent across site, receipt PDF, email and footer.
Compliance Item | Status | Evidence | Gap | Action Required
Trust Registration (E-30560) | Verified | Consistent across site, receipt HTML, PDF, email footer | None | None
12A (47522) | Verified | Receipt PDF + legal pages | None | None
80G (CITE80G9792014-152016-17) | Verified | Receipt PDF, receipt email body, footer | None | None
CSR-1 (CSR00089305) | Verified | Legal / CSR pages | None | None
DARPAN (MH/2024/0457296) | Verified | Legal pages | None | None
PAN (AACTR4271L) | Verified | Receipt PDF; two-stage donor PAN capture | None | None
Receipt wording | Verified | 'Provisional receipt; Form 10BE by 31 May' verbatim in receipt-pdf.ts + email | None | CA confirm format (recommended)
Donation records | Verified | Immutable ledger; 13 rows; audit trail | None | None
Donor PAN masking | Verified | maskPan() on display | None | None
Form 10BD/10BE issuance | Pending (operational) | Correctly framed to donors as 'by 31 May' | Year-end manual/roadmap task | Issue at year-end

## 10. Assets Needed
SHEET 10 — ASSETS REQUIRED FROM FOUNDER
Content/assets still needed. None block the technical launch; receipt-format confirmation + impact report are highest-value for donor trust.
Asset | Purpose | Priority | Blocking Launch | Status
PHOTOS
Tobler | Hero subject / story | P2 | No | Pending
Founder | About / credibility | P2 | No | Pending
Family | About / story | P3 | No | Pending
Team | Staff, volunteers, vets | P2 | No | Pending
Shelter | Facility, kennels, recovery areas | P2 | No | Pending
Rescue | In-action rescue shots | P2 | No | Pending
Feeding Drives | Programme proof | P2 | No | Pending
Before/After Recovery | Impact proof (paired) | P2 | No | Pending
DOCUMENTS
Impact Report | Numbers: animals helped, rescues, spend | P1 | No | Pending
Sample Receipt (from CA) | Confirm generated PDF matches preferred format | P1 | No | Pending
CSR Case Studies | Corporate donor conversion | P2 | No | Pending
Partner Logos | Credibility / partnerships | P2 | No | Pending
CONTENT
Testimonials | Donor/partner/beneficiary trust | P2 | No | Pending
Stories | 3-5 rescue narratives | P2 | No | Pending
Updates | Recent milestones for homepage/newsletter | P3 | No | Pending

## 11. Pending Tasks
SHEET 11 — PENDING TASKS MASTER LIST
All open tasks grouped A (before launch) / B (within 30 days) / C (future).
Task | Owner | Priority | Est. Time | Blocking Launch | Status
A. MUST COMPLETE BEFORE LAUNCH
Add live Razorpay keys + live webhook secret to Vercel | Founder | P0 | 15 min | Yes | Pending
Run one test-card donation; confirm both emails + PDF | Founder | P0 | 15 min | Yes | Pending
DNS cutover (A + CNAME) at registrar | Founder | P0 | 15 min + propagation | Yes | Pending
Rotate secrets shared in chat | Founder | P0 | 35-45 min | Yes (security) | Pending
Verify Razorpay + registrar account access | Founder | P0 | 10 min | Yes | Pending
Reset demo/test data (say 'go') | Founder | P1 | 5 min | Recommended | Pending
Approve final receipt format with CA | Founder | P1 | - | Recommended | Pending
B. RECOMMENDED WITHIN 30 DAYS AFTER LAUNCH
Install analytics (privacy-friendly) | Founder | P2 | 30 min | No | Pending
Add error/uptime monitoring + alerting | Founder | P2 | 1 hr | No | Pending
Rate-limit / harden admin token; remove 'M4' note | Founder/Dev | P2 | 1 hr | No | Pending
Fix donor-email enumeration on /api/compliance | Dev | P2 | 1 hr | No | Pending
Add real photography & impact content | Founder | P2 | - | No | Pending
C. FUTURE ENHANCEMENTS
Donor nurture / monthly impact emails | Dev | P3 | - | No | Pending (roadmap)
Automate year-end Form 10BD/10BE issuance | Dev | P3 | - | No | Pending (roadmap)
WhatsApp / CRM automations | Dev | P3 | - | No | Pending (roadmap)
Email retry queue (Resend outage resilience) | Dev | P3 | - | No | Pending (roadmap)

## 12. Founder Dashboard
SHEET 12 — FOUNDER ACTION DASHBOARD (DAILY)
The only sheet to look at daily. When all 'Blocking Launch = Yes' rows are Done -> GO.
Action | Owner | Due | Blocking Launch | Current Status
Add live Razorpay keys + webhook secret | Founder | Before launch | Yes | Pending
Run one test-card donation + verify 2 emails + PDF | Founder | Before launch | Yes | Pending
DNS cutover (A + CNAME) | Founder | Before launch | Yes | Pending
Rotate shared secrets (Supabase/Resend/admin/webhook) | Founder | Before launch | Yes | Pending
Verify Razorpay + registrar access | Founder | Before launch | Yes | Pending
Reset demo/test data | Founder | Launch day | Recommended | Pending
CA confirms receipt format | Founder | Before/at launch | Recommended | Pending
Install analytics + monitoring | Founder | Within 30 days | No | Pending
Add real photos + impact report | Founder | Within 30 days | No | Pending

## 13. Disaster Recovery
SHEET 13 — DISASTER RECOVERY
Architectural strength: webhook is source of truth; money/receipt persistence is decoupled from email; Razorpay retries + DB idempotency self-reconcile.
Scenario | Current Behaviour | Business Impact | Recovery Process | Recovery Time
Razorpay down | /api/donate throws 500; no order, no charge | Donor can't donate during outage; no money taken w/o record | Wait for Razorpay; donor retries; check status page
Resend down | Donation recorded + receipt generated; email throws -> caught, logged; webhook still 200 | Money + receipt safe; donor misses email | Re-send receipt from admin; consider retry queue | Minutes (manual re-send)
Supabase down | DB writes throw; /api/donate 500 (no charge); webhook 500 -> Razorpay retries | Donations pause cleanly; no orphan charges | Wait for Supabase; webhook retries reconcile captures
Vercel down | Site + APIs unavailable | Full outage (donations, forms, admin) | Wait for Vercel; code+env preserved; instant redeploy/rollback; no data loss (DB on Supabase)
DNS failure | rkmfoundation.com won't resolve; *.vercel.app still works | Branded domain unreachable; vercel.app donations still work | Fix A/CNAME; SSL re-issues automatically | Minutes-hours (propagation)
Webhook failure (5xx/transient) | Returns 500 -> Razorpay auto-retries; UNIQUE constraint prevents double-processing | Receipt/email delayed minutes; no duplication | Self-healing; monitor Vercel logs for repeats | Auto (retry window)
Admin token leak | Anyone with token can view donor data/exports | Donor PII exposure risk | Immediately rotate ADMIN_ACCESS_TOKEN + redeploy (invalidates old); review access | < 10 min

## Final Output
FINAL OUTPUT — RKM FOUNDATION LAUNCH
1. GO / NO-GO
Verdict | NO-GO today for real donations. Engineering is sound; blockers are operational.
2. EXACT LAUNCH BLOCKERS
Blocker 1 | Razorpay in TEST mode - no live keys.
Blocker 2 | Donor receipt + acknowledgement emails not verified end-to-end in a real inbox.
Blocker 3 | DNS not cut over to rkmfoundation.com.
3. EXACT FOUNDER TASKS REMAINING
1 | Add live Razorpay keys + live webhook secret -> redeploy.
2 | Run one test-card donation; confirm both emails + PDF receipt land.
3 | Cut over DNS (A + CNAME).
4 | Rotate the secrets shared in chat.
5 | Reset demo data on 'go'; CA confirms receipt format.
4. ESTIMATED HOURS TO LAUNCH
Hours | ~2-3 hours focused founder work (45m rotation, 30m live keys+webhook, 30m test+verify, 15m DNS, 15m demo reset).
5. CONFIDENCE SCORE
Confidence | 88% - high confidence system is launch-ready once operational steps done. Remaining 12% = the single unverified live card->webhook->inbox path + DNS/live-key first-run risk.
6. TOP 10 RISKS
R1 | Live card->webhook->receipt-email path unverified end-to-end (only a real test donation closes it).
R2 | Live secrets shared in chat not yet rotated.
R3 | Razorpay still in TEST mode at launch if keys not switched.
R4 | DNS misconfiguration delaying domain + SSL.
R5 | Admin auth is a single shared static token (no MFA/lockout).
R6 | Donor-email enumeration via /api/compliance.
R7 | No monitoring/alerting - outages found only via manual log checks.
R8 | Resend domain verification lapse -> silent email failure.
R9 | Email send has no retry queue (one Resend outage = missed emails until manual re-send).
R10 | 7 historical paid test rows lack receipts (benign; must run demo reset before launch).
7. TOP 10 PRIORITIES
P1 | Switch Razorpay to live keys + live webhook secret.
P2 | Run + verify one test-card donation (both emails + PDF).
P3 | Rotate all secrets shared in chat.
P4 | DNS cutover + confirm SSL issues.
P5 | Verify Razorpay + registrar account access.
P6 | Reset demo/test data.
P7 | CA confirms receipt format.
P8 | Harden admin token (rate-limit; remove M4 note).
P9 | Install analytics + monitoring.
P10 | Add real photography + impact report.
8. ONE-PAGE FOUNDER SUMMARY
Where it stands | The site is built, the donation backend is sound, and compliance is in place. It is NOT live for real money yet - three operational steps remain: live payment keys, one verified test donation, and DNS cutover. Plus rotate the secrets shared in chat.
What's proven | Donation ledger, webhook idempotency (DB-enforced), gapless receipt numbering, receipt PDF, form acknowledgements, audit trail, all registrations (12A/80G/CSR-1/DARPAN/PAN). Data integrity clean: 0 orphans, 0 duplicate receipts/refs.
The one true gap | The donor receipt + thank-you emails are fully built and every component is proven, but no real card payment has confirmed they actually arrive. One test donation closes this.
Decision | NO-GO today; flips to GO after live keys + one verified test donation + DNS. ~2-3 hours of work. Confidence 88%.
Handover-ready | This workbook is suitable for immediate handover to a developer, agency, CTO, auditor, board member, or compliance consultant.