## Read First
RKM FOUNDATION — FINAL DEPLOYMENT REVIEW
Status reality check — read before the other tabs
Nothing has been deployed yet | No changes have been implemented on rkmfoundation.com during this engagement. No site code, content, or Razorpay settings were modified. This work has been audit, validation and planning — delivered as workbooks. I have no repo / CMS / dashboard / deploy access, so I cannot and did not change the live site.
So what is this file? | A readiness review of the EXISTING recommendations (no new findings). It tells you, for each already-documented change: is it ready to build & ship, does it need a visual preview, does it need you, and what's the deploy risk — plus the verified status of the donation system.
Honest framing of 'deploy' | 'Ready to deploy today' means: no blockers, low risk, a developer could build and ship it now. It does NOT mean it is already built. Every item still has to be implemented by you or a developer.
Source | All items trace to the 39 findings in RKM_Foundation_Master_Workbook.xlsx. This review only re-classifies them for execution; it adds no new audits, strategies or ideas.

## 1. Change Inventory
Phase 1 — Forensic Change Inventory
Files actually changed on the site this engagement: NONE. Below: (A) deliverables produced, (B) recommended changes, all status = Not implemented.
A. Files actually produced this engagement (analysis documents — not site changes)
File | Type | Purpose | Status
RKM_Foundation_Audit.xlsx | Workbook | Master prompt, scorecard, strategy deep-dives, build kit, payment test runbook | Delivered
RKM_Foundation_Master_Workbook.xlsx | Workbook | 39-finding register + category views + roadmap + owner decisions | Delivered
RKM_FINAL_DEPLOYMENT_REVIEW.xlsx | Workbook | This deployment-readiness review | Delivered
(memory) project notes | Notes | Engagement context for future sessions | Saved
B. Recommended site changes — implementation status (Old State = current live; New State = recommendation)
ID / Page | Category | Old State (current live) | New State (recommended) | Status
REV-1 · Donate / Razorpay | Donation | Monthly donations support CARDS ONLY — no UPI Autopay / Netbanking / Wallet on the subscription checkout (one-time has all). | Enable UPI Autopay (e-mandate) for Subscriptions in Razorpay, then re-test. | Not implemented
REV-2 · Donate | Donation | Monthly is not the default ask — the donate widget defaults to One-Time. | Make Monthly the default tab; one-time secondary. | Not implemented
REV-3 · New club page | Donation | No monthly donor club / identity — recurring is a transaction, not a membership. | Launch 'Guardian Circle' with identity, welcome kit, monthly updates. | Not implemented
REV-4 · Donate | Donation | No major-gift / HNI path (₹50k–₹5L donors have no tailored route). | Add sponsor-a-kennel / fund-a-route / name-a-programme + personal contact + stewardship. | Not implemented
REV-5 · Downloads / Legal / CSR | Compliance | No published audited financials or annual report (site claims 'every rupee accounted for' + annual audit). | Publish audited financials + 1-page annual impact report + program/admin % split (PDF). | Not implemented
REV-6 · CSR page | Compliance | CSR page is strong but lacks named corporate partners, a sample utilisation certificate, and impact numbers. | Add 1-2 partner case studies, a sample utilisation cert, audited financials; build a CSR pitch deck + outbound. | Not implemented
REV-7 · Sitewide | Compliance | No third-party validation listing/badge (e.g. GiveIndia/Give.do; Candid/Charity-Navigator equivalents). | List + get verified on GiveIndia/Give.do; display the badge on home/donate/CSR. | Not implemented
CVR-1 · Donate / Razorpay | Donation | Checkout opens slowly: 'Opening secure payment…' hangs ~5-10s (one-time AND monthly) before Razorpay appears. | Pre-create the Razorpay order on form focus; show progress; target <1.5s. | Not implemented
CVR-2 · Donate / Razorpay | Donation | Payment COMPLETION not verified (we don't process real payments). | Run ₹100 one-time + ₹100 monthly tests end-to-end (see runbook). | Not implemented
CVR-3 · Home + Donate | UI | Social proof not where people decide — testimonials live on /media, absent from home/donate. | Surface 2-3 independent donor testimonials + a donor count on home & donate. | Not implemented
CVR-4 · Home | Content | No specific live rescue cases with funding goals — only generic 'an animal is waiting'. | Add an 'active cases' module (name, photo, ₹ goal, progress bar). | Not implemented
CVR-5 · Donate | Donation | ₹1,000 minimum donation filters out small / first-time donors. | A/B test a ₹100-₹500 entry tier with an upgrade path. | Not implemented
CVR-6 · Donate | Donation | Returning to the donate page auto-reopens the previous Razorpay checkout from prior state. | Clear checkout state on page load. | Not implemented
CVR-7 · Donate | UI | No 80G tax-savings framing at the point of decision (80G = 50% deduction). | Add an 80G savings line/calculator near the CTA. | Not implemented
UX-1 · Donate | Content | Monthly tier descriptions aren't reframed for recurring (still read 'for 2 weeks' / 'for a month'). | Reframe monthly amounts as ongoing ('₹500/mo keeps one dog fed every day'). | Not implemented
UX-2 · Home / About | UI | The Mundhra family + Tobler origin (a strong trust anchor) is under-leveraged. | Add a short founder video + family photo near the primary CTA. | Not implemented
UX-3 · Volunteer page | UI | Volunteer journey is a bare contact form — no roles, locations, schedule, commitment, or onboarding. | Rebuild volunteer page (roles, Thane/Mumbai drive calendar, onboarding). | Not implemented
UX-4 · Sitewide | Content | Hindi version is 'coming soon' / incomplete. | Complete Hindi localization for the core donor journey. | Not implemented
RET-1 · Post-donation / email | Content | No productised post-gift journey (thank-you → receipt → first impact update). | Build the journey: instant thank-you + receipt, impact update <48h, then monthly. | Not implemented
RET-2 · Email / WhatsApp | Content | No monthly impact update to recurring donors. | Monthly photo + one rescue story via WhatsApp (existing opt-in) + email. | Not implemented
RET-3 · Donate / subscription | Donation | No 'pause instead of cancel' or annual upgrade ask (cancel-anytime exists). | Add pause option + a once-a-year step-up ask. | Not implemented
RET-4 · CRM / data | Analytics | No lapsed-donor win-back program. | After the donor-data export (CI-1), build a win-back list + sequence. | Not implemented
CI-1 · Razorpay / data | Analytics | No donor-economics baseline (retention, recurring %, avg gift, frequency, LTV). | Export Razorpay 24-mo payments + subscriptions; I'll run the full analysis. | Not implemented
CI-2 · Home + Media | Content | Some /media testimonials are team-affiliated (e.g. Ankit Palan is Core Management; the vet praises 'Brinda' = Brinda Palan, Core Management). | Lead with independent donor testimonials; label affiliated voices honestly. | Not implemented
CI-3 · Analytics | Analytics | No web analytics access provided — traffic, sources, and funnel drop-off can't be verified. | Share read access to GA4 / analytics; confirm analytics is even installed. | Not implemented
CI-4 · Data | Analytics | Donor personas are built from the site, not quantified against real donor data. | Re-derive segments from the donor-data export. | Not implemented
TEC-1 · Sitewide | Performance | Three Google font families load render-blocking from Google (Inter + DM Sans + Noto Sans Devanagari). | Consolidate to 1-2 families; self-host / preload; subset Devanagari. | Not implemented
TEC-2 · Home / images | Performance | Hero/section images served as raw .jpg rather than next-gen formats. | Serve WebP/AVIF via Next.js Image; confirm sizes. | Not implemented
TEC-3 · Server | Security | Security headers (HSTS/CSP/etc.) not verified. | Audit response headers; add HSTS + a sensible CSP. | Not implemented
TEC-4 · /admin, /prototype | Security | /admin, /prototype, /prototype-v2 paths exist (disallowed in robots.txt). | Confirm these are access-controlled + noindex; don't expose staging. (Not probed by us.) | Not implemented
TEC-5 · Sitewide | Performance | Site is a modern Next.js app; all homepage resources returned 200/304 with no console errors on load. | Strength — keep | Already live (strength)
SEO-1 · Sitewide | SEO | robots.txt present and correct, references the sitemap; sitemap.xml exists. | Strength — keep | Already live (strength)
SEO-2 · Sitewide | SEO | Per-page meta titles, descriptions and Open Graph tags are present and well-written. | Strength — keep | Already live (strength)
SEO-3 · New city pages | SEO | No city/cause landing pages; thin content limits organic acquisition. | Build cause + city pages (Thane/Mumbai) targeting donor intent. | Not implemented
SEO-4 · Sitewide | SEO | Structured data (JSON-LD Organization/NGO) not confirmed on pages. | Add Organization + relevant schema; validate in Rich Results Test. | Not implemented
SEO-5 · Blog | Content | Only one blog post (Tobler); no content cadence. | Monthly rescue-story cadence; repurpose to social. | Not implemented
ACC-1 · Sitewide | Accessibility | Images carry descriptive alt text. | Strength — keep | Already live (strength)
ACC-2 · Donate | Accessibility | Full WCAG 2.1 AA (keyboard, focus order, screen reader, touch targets) not audited. | Run an axe / Lighthouse a11y audit on the donate flow; fix blockers. | Not implemented
ACC-3 · Sitewide | Accessibility | Low-contrast light-grey body text observed (e.g. the faded sub-line on home/donate). | Verify contrast ratios; darken body text to meet AA (4.5:1). | Not implemented

## 2. Preview Readiness
Phase 2 — Preview Readiness
Can a preview be built now? READY = yes. NOT READY = missing owner content/data. BLOCKED = depends on payment/3rd-party/access.
Classification | ID | Item | Why
READY FOR PREVIEW | CVR-3 | Social proof not where people decide — testimonials live on /media, absent from home/donate. | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | CVR-6 | Returning to the donate page auto-reopens the previous Razorpay checkout from prior state. | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | CVR-7 | No 80G tax-savings framing at the point of decision (80G = 50% deduction). | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | UX-1 | Monthly tier descriptions aren't reframed for recurring (still read 'for 2 weeks' / 'for a month'). | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | UX-3 | Volunteer journey is a bare contact form — no roles, locations, schedule, commitment, or onboarding. | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | REV-2 | Monthly is not the default ask — the donate widget defaults to One-Time. | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | REV-3 | No monthly donor club / identity — recurring is a transaction, not a membership. | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | RET-1 | No productised post-gift journey (thank-you → receipt → first impact update). | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | RET-2 | No monthly impact update to recurring donors. | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | RET-3 | No 'pause instead of cancel' or annual upgrade ask (cancel-anytime exists). | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | CI-2 | Some /media testimonials are team-affiliated (e.g. Ankit Palan is Core Management; the vet praises 'Brinda' = Brinda Palan, Core Management). | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | TEC-1 | Three Google font families load render-blocking from Google (Inter + DM Sans + Noto Sans Devanagari). | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | TEC-2 | Hero/section images served as raw .jpg rather than next-gen formats. | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | SEO-4 | Structured data (JSON-LD Organization/NGO) not confirmed on pages. | Draft/spec complete; a developer can build a preview
READY FOR PREVIEW | ACC-3 | Low-contrast light-grey body text observed (e.g. the faded sub-line on home/donate). | Draft/spec complete; a developer can build a preview
NOT READY FOR PREVIEW | REV-4 | No major-gift / HNI path (₹50k–₹5L donors have no tailored route). | Offer design + stewardship copy needed
NOT READY FOR PREVIEW | REV-5 | No published audited financials or annual report (site claims 'every rupee accounted for' + annual audit). | Needs audited financials documents
NOT READY FOR PREVIEW | REV-6 | CSR page is strong but lacks named corporate partners, a sample utilisation certificate, and impact numbers. | Needs partner names + sample cert
NOT READY FOR PREVIEW | CVR-4 | No specific live rescue cases with funding goals — only generic 'an animal is waiting'. | Needs real case data + photos
NOT READY FOR PREVIEW | UX-2 | The Mundhra family + Tobler origin (a strong trust anchor) is under-leveraged. | Needs founder video recorded
NOT READY FOR PREVIEW | UX-4 | Hindi version is 'coming soon' / incomplete. | Needs Hindi translation
NOT READY FOR PREVIEW | SEO-3 | No city/cause landing pages; thin content limits organic acquisition. | Needs page content written
NOT READY FOR PREVIEW | SEO-5 | Only one blog post (Tobler); no content cadence. | Needs story content written
BLOCKED | REV-1 | Monthly donations support CARDS ONLY — no UPI Autopay / Netbanking / Wallet on the subscription checkout (one-time has all). | Needs UPI Autopay enabled in Razorpay first
BLOCKED | REV-7 | No third-party validation listing/badge (e.g. GiveIndia/Give.do; Candid/Charity-Navigator equivalents). | Third-party listing/verification is external
BLOCKED | CVR-1 | Checkout opens slowly: 'Opening secure payment…' hangs ~5-10s (one-time AND monthly) before Razorpay appears. | Payment-integration change — verify in Razorpay first
BLOCKED | CVR-2 | Payment COMPLETION not verified (we don't process real payments). | It's a test, not a previewable build
BLOCKED | CI-1 | No donor-economics baseline (retention, recurring %, avg gift, frequency, LTV). | Needs the Razorpay data export
BLOCKED | CI-3 | No web analytics access provided — traffic, sources, and funnel drop-off can't be verified. | Needs analytics access
BLOCKED | CI-4 | Donor personas are built from the site, not quantified against real donor data. | Needs donor data
BLOCKED | RET-4 | No lapsed-donor win-back program. | Needs donor data
BLOCKED | TEC-3 | Security headers (HSTS/CSP/etc.) not verified. | Needs server/header access
BLOCKED | TEC-4 | /admin, /prototype, /prototype-v2 paths exist (disallowed in robots.txt). | Needs access-control verification
BLOCKED | ACC-2 | Full WCAG 2.1 AA (keyboard, focus order, screen reader, touch targets) not audited. | Needs a11y tooling run

## 3. Visual Review
Phase 3 — Visual Impact Review
Benchmark: victorfuruya.com (editorial, full-bleed .webp photography, oversized type, deep negative space). NOTE: no UI changes have been implemented, so this compares the CURRENT site.
Dimension | Achieved (current live site) | Unfinished (proposed, not yet built)
Typography | Large, confident headlines ('Your generosity turns care into action') — already editorial in spirit. | Type scale not as oversized/dramatic as the reference; consistency once 3 font families are consolidated (TEC-1).
Layout | Clean, sectioned layout with a strong hero and clear CTAs. | Reference's full-bleed, asset-led sections; live rescue-case module (CVR-4) not built.
Spacing | Generous whitespace and breathing room on key pages. | Editorial 'air' is good but not as expansive/scroll-driven as the reference.
Photography | Real, emotive animal photography in the hero and sections. | Served as .jpg not next-gen .webp (TEC-2); not full-bleed cinematic throughout like the reference.
Emotional storytelling | Authentic founder story (Tobler) and warm, human copy. | Proof layer (impact numbers, live cases, on-page testimonials) not yet surfaced (CVR-3/CVR-4).
Editorial feel | Strong — copy and palette feel considered, not templated. | Content depth (one blog post) limits the editorial 'magazine' effect (SEO-5).
Premium feel | Trust badges, clean donate UX and palette read credible. | Founder video + richer proof (UX-2) would lift it further; low-contrast text undercuts polish (ACC-3).
Mobile experience | Responsive layout present. | Mobile donate + checkout flow NOT yet verified end-to-end (see Donation review); contrast/perf fixes pending.

## 4. Deployment Review
Phase 4 — Deployment Review
Only site-deployable changes shown (owner/data items live in tab 6). Class: SAFE TO DEPLOY / REVIEW FIRST / DO NOT DEPLOY.
ID | Item | Risk | Rollback | Dependencies | Class
CVR-3 | Social proof not where people decide — testimonials live on /media, absent from home/donate. | Low | Easy | Have testimonials (Media) | SAFE TO DEPLOY
CVR-7 | No 80G tax-savings framing at the point of decision (80G = 50% deduction). | Low | Easy | None | SAFE TO DEPLOY
UX-1 | Monthly tier descriptions aren't reframed for recurring (still read 'for 2 weeks' / 'for a month'). | Low | Easy | Copy only | SAFE TO DEPLOY
UX-3 | Volunteer journey is a bare contact form — no roles, locations, schedule, commitment, or onboarding. | Low | Easy | Volunteer content exists | SAFE TO DEPLOY
RET-3 | No 'pause instead of cancel' or annual upgrade ask (cancel-anytime exists). | Low | Easy | Subscription copy/flow | SAFE TO DEPLOY
TEC-1 | Three Google font families load render-blocking from Google (Inter + DM Sans + Noto Sans Devanagari). | Low | Easy | Dev font config | SAFE TO DEPLOY
TEC-2 | Hero/section images served as raw .jpg rather than next-gen formats. | Low | Easy | Image pipeline | SAFE TO DEPLOY
SEO-4 | Structured data (JSON-LD Organization/NGO) not confirmed on pages. | Low | Easy | Dev adds schema | SAFE TO DEPLOY
ACC-3 | Low-contrast light-grey body text observed (e.g. the faded sub-line on home/donate). | Low | Easy | CSS contrast | SAFE TO DEPLOY
CVR-6 | Returning to the donate page auto-reopens the previous Razorpay checkout from prior state. | Low-Med | Easy | Donate-page state (payment-adjacent) | REVIEW FIRST
REV-2 | Monthly is not the default ask — the donate widget defaults to One-Time. | Med | Easy | Touches donate widget default | REVIEW FIRST
REV-3 | No monthly donor club / identity — recurring is a transaction, not a membership. | Med | Medium | Depends on REV-1 (UPI) for enrolment | REVIEW FIRST
CVR-4 | No specific live rescue cases with funding goals — only generic 'an animal is waiting'. | Med | Easy | Needs real case data/photos | REVIEW FIRST
RET-1 | No productised post-gift journey (thank-you → receipt → first impact update). | Med | Medium | ESP/automation + consent | REVIEW FIRST
RET-2 | No monthly impact update to recurring donors. | Med | Medium | WhatsApp/ESP + content | REVIEW FIRST
REV-4 | No major-gift / HNI path (₹50k–₹5L donors have no tailored route). | Med | Medium | Major-gift offer + stewardship | REVIEW FIRST
SEO-3 | No city/cause landing pages; thin content limits organic acquisition. | Low-Med | Easy | New page content | REVIEW FIRST
CVR-1 | Checkout opens slowly: 'Opening secure payment…' hangs ~5-10s (one-time AND monthly) before Razorpay appears. | Med-High | Medium | Razorpay order/integration — test first | DO NOT DEPLOY
REV-1 | Monthly donations support CARDS ONLY — no UPI Autopay / Netbanking / Wallet on the subscription checkout (one-time has all). | High | Hard | Razorpay UPI Autopay config + retest — payments | DO NOT DEPLOY

## 5. Donation System Review
Phase 5 — Donation System Review
Only what was actually observed. Not guessed. If not verified, marked Unverified.
Component | Status | Evidence | Note
Razorpay (checkout) | Verified | Browser 19 Jun | Checkout opens and loads payment options (slowly, ~5-10s).
Monthly Donations | Verified | Browser 19 Jun | Creates a real subscription: ₹X now then ₹X/month, card linked per RBI e-mandate.
UPI Autopay | Verified — NOT available | Browser 19 Jun | Subscription checkout offers CARDS ONLY. No UPI Autopay / Netbanking / Wallet.
Receipts (80G/instant) | Unverified | Could not complete payment | Site claims instant 80G receipt; not confirmed (no completed transaction).
Emails (confirmation) | Unverified | Could not complete payment | Not confirmed end-to-end.
PAN Capture | Verified | Browser 19 Jun | Optional PAN field present on the donate form for 80G.
Compliance (12A/80G/CSR-1/DARPAN) | Verified | Site downloads + Legal page | Certificates downloadable; governance/anti-fraud policies published.
Donor Records | Unverified | No dashboard/data access | Cannot confirm how donations are recorded/attributed.

## 6. Final Execution Board
Phase 6 — Final Execution Board
Each item appears once. No strategy, no new recommendations — just where each existing item sits.
1. Ready to Build & Ship Today (no blockers, low risk)
CVR-3 | Social proof not where people decide — testimonials live on /media, absent from home/donate.
CVR-6 | Returning to the donate page auto-reopens the previous Razorpay checkout from prior state.
CVR-7 | No 80G tax-savings framing at the point of decision (80G = 50% deduction).
UX-1 | Monthly tier descriptions aren't reframed for recurring (still read 'for 2 weeks' / 'for a month').
UX-3 | Volunteer journey is a bare contact form — no roles, locations, schedule, commitment, or onboarding.
RET-3 | No 'pause instead of cancel' or annual upgrade ask (cancel-anytime exists).
TEC-1 | Three Google font families load render-blocking from Google (Inter + DM Sans + Noto Sans Devanagari).
TEC-2 | Hero/section images served as raw .jpg rather than next-gen formats.
SEO-4 | Structured data (JSON-LD Organization/NGO) not confirmed on pages.
ACC-3 | Low-contrast light-grey body text observed (e.g. the faded sub-line on home/donate).
2. Needs Preview Review (build, then eyeball before shipping)
REV-2 | Monthly is not the default ask — the donate widget defaults to One-Time.
REV-3 | No monthly donor club / identity — recurring is a transaction, not a membership.
CVR-4 | No specific live rescue cases with funding goals — only generic 'an animal is waiting'.
RET-1 | No productised post-gift journey (thank-you → receipt → first impact update).
RET-2 | No monthly impact update to recurring donors.
UX-2 | The Mundhra family + Tobler origin (a strong trust anchor) is under-leveraged.
REV-4 | No major-gift / HNI path (₹50k–₹5L donors have no tailored route).
CI-2 | Some /media testimonials are team-affiliated (e.g. Ankit Palan is Core Management; the vet praises 'Brinda' = Brinda Palan, Core Management).
3. Needs Owner Action (you / dashboard / data / legal / 3rd-party)
REV-1 | Monthly donations support CARDS ONLY — no UPI Autopay / Netbanking / Wallet on the subscription checkout (one-time has all).
CVR-1 | Checkout opens slowly: 'Opening secure payment…' hangs ~5-10s (one-time AND monthly) before Razorpay appears.
CVR-2 | Payment COMPLETION not verified (we don't process real payments).
REV-5 | No published audited financials or annual report (site claims 'every rupee accounted for' + annual audit).
REV-6 | CSR page is strong but lacks named corporate partners, a sample utilisation certificate, and impact numbers.
REV-7 | No third-party validation listing/badge (e.g. GiveIndia/Give.do; Candid/Charity-Navigator equivalents).
CI-1 | No donor-economics baseline (retention, recurring %, avg gift, frequency, LTV).
CI-3 | No web analytics access provided — traffic, sources, and funnel drop-off can't be verified.
CI-4 | Donor personas are built from the site, not quantified against real donor data.
RET-4 | No lapsed-donor win-back program.
TEC-3 | Security headers (HSTS/CSP/etc.) not verified.
TEC-4 | /admin, /prototype, /prototype-v2 paths exist (disallowed in robots.txt).
ACC-2 | Full WCAG 2.1 AA (keyboard, focus order, screen reader, touch targets) not audited.
UX-4 | Hindi version is 'coming soon' / incomplete.
4. Future Enhancements (lower priority / longer horizon)
CVR-5 | ₹1,000 minimum donation filters out small / first-time donors.
SEO-3 | No city/cause landing pages; thin content limits organic acquisition.
SEO-5 | Only one blog post (Tobler); no content cadence.

## 7. Final Answer
Phase 7 — Final Answer
The four questions, answered from what exists today.
1. What can be deployed today? | Nothing is built yet, but these have NO blockers and a developer could build + ship immediately (low risk, reversible): on-page social proof (CVR-3), 80G tax framing (CVR-7), monthly copy reframe (UX-1), volunteer page (UX-3), pause/upgrade options (RET-3), font consolidation (TEC-1), image optimisation (TEC-2), schema (SEO-4), contrast fix (ACC-3), and clearing the checkout-reopen state (CVR-6).
2. What should NOT be deployed today? | Anything touching payments until tested: enabling UPI Autopay (REV-1) and the checkout-speed change (CVR-1) are DO NOT DEPLOY until the ₹100 tests + Razorpay verification pass. Default-monthly (REV-2), the club page (REV-3), live cases (CVR-4) and donor-comms automations (RET-1/RET-2) are REVIEW FIRST — build, preview, then ship.
3. What is still unverified? | Payment COMPLETION, 80G receipt delivery, confirmation emails, and donor-record attribution (no completed transaction / no dashboard access). Also unverified: donor economics (no export), analytics/funnel (no access), full WCAG accessibility (no tooling), and security headers. These are the HYPOTHESIS items — see Donation Review (tab 5) and the master workbook.
4. Fastest path from 4/10 to 7/10 readiness | Three moves, in order: (1) VERIFY the donation system — run the ₹100 one-time + monthly tests and confirm UPI Autopay in Razorpay (turns the biggest unknowns green). (2) SHIP the no-blocker proof + trust items (impact numbers, on-page social proof, 80G framing, published financials). (3) TURN ON the recurring engine — UPI Autopay + default-monthly + the Guardian Circle + monthly updates. That sequence closes the verification gap and the two lowest scores (recurring 4/10, proof) — the bulk of the 4→7 jump.