## 1. Executive Summary
Field | Detail
Organisation | RKM Foundation — registered charitable trust, India (Thane West, Maharashtra). Animal welfare: rescue, feed, treat, sterilise, vaccinate, rehome. Founded 2014.
Mission (working — confirm) | RKM Foundation rescues, feeds, heals, and shelters animals in need across India. [NEEDS DATA: confirm canonical one-liner]
Positioning (the spine) | 'Most people walk past. We're who they call when someone doesn't.'
Website vision | One of the most exceptional nonprofit websites of 2026 — award-credible (Awwwards/CSS Design Awards/FWA) AND a high-performing, trustworthy donation engine.
Definition of success | (1) Distinctive signature concept implemented; (2) maximised recurring donations, measured; (3) CWV good at field p75, WCAG 2.2 AA, PCI SAQ-A, DPDP/GDPR compliant.
Signature concept | 'The Ones Who Didn't Walk Past' (spine) + 'Tobler's Ledger' (proof signature) + 'Long Night to First Light' (art-direction light).
Top risks | No analytics baseline yet; cookie consent non-compliant; live secrets exposed (rotate); thin trust/proof density; revenue concentration (no recurring/legacy channels).
Top opportunities | Monthly-first + Guardian program; Legacy giving (~55% of RSPCA income); Tribute & P2P; authentic Tobler/rescue storytelling.
Highest-priority next action | RKMF-004 (compliant cookie consent) -> RKMF-005 (deploy analytics): unblocks all measurement. RKMF-044 (legacy) = top new build.
Research status | COMPLETE (audit, fundraising, benchmark, creative direction, experience design).
Phase from here | Wireframes -> Visual design -> Build. No further research.
Issue count | 52 issues (RKMF-001..052): 6 DONE, 1 IN-PR, 28 OPEN, 11 FACT-BLOCKED, 4 DATA-BLOCKED, 1 BUILD-BLOCKED, 1 FOUNDER.

## 2. Source of Truth
Item | Value | Confidence / Source
Cause / sector | Animal welfare — rescue, feed, treat, sterilise, vaccinate, rehome | Confirmed
Who we serve / where | Street & abandoned animals; Thane West / Mumbai metro, Maharashtra | Confirmed (code/site)
Donor base | India, INR; English + Hindi (/hi). NRI/diaspora & FCRA scope | [NEEDS DATA: FCRA/NRI]
Founded / origin | 2014; began with founders' pug Tobler + strangers at the vet who 'couldn't walk past' | Confirmed (site)
Trust Registration | E-30560 | Confirmed
PAN | AACTR4271L | Confirmed
12A | 47522 | Confirmed
80G | CITE80G9792014-152016-17 | Confirmed
CSR-1 | CSR00089305 | Confirmed
NITI Aayog DARPAN | MH/2024/0457296 | Confirmed
Address / contact | 201, 2nd Floor, Bldg 4, Paramos Tower, Vasant Lawns, Majiwada, Thane West 400601; info@rkm.support; +91 99207 80005 | Confirmed
Tech stack | Next.js 14 (App Router), React 18, Tailwind; Vercel host; Supabase DB; Razorpay; Resend; pdf-lib. Bilingual EN + /hi. | Confirmed (repo)
Donation processing | Razorpay (orders + on-the-fly monthly subscriptions); webhook = source of truth; idempotent; gapless 80G receipt PDFs; instant email | Confirmed (repo)
Analytics / baseline | NONE installed -> no funnel baseline exists | Confirmed (gap)
Brand tokens | Ink #111111, Snow/Mist #F5F5F5, Copper #B89245 (dark #8F6A2A, light #E6D2A0); font Inter (+Noto Sans Devanagari) | Confirmed (repo)
Testimonials | 5 real, named, w/ photos: Raghav Daga, Shweta Desai, Ankit Palan, Aditya Mohatta, Dr. Kiran Shelar | Confirmed (repo)
Impact numbers / cost math | Animals rescued/treated/sterilised/fed/rehomed + cost-per-outcome | [NEEDS DATA]
Financials / fund-allocation % | Audited financials, where-money-goes % | [NEEDS DATA]
Board / leadership | Named founders + trustees + consent | [NEEDS DATA]
Active campaign | Any live matching/challenge grant | [NEEDS DATA]

## 3. Creative Direction
Element | Decision | Rationale / notes
Chosen concept | 'The Ones Who Didn't Walk Past' (spine) | RKM exists because strangers couldn't walk past a hurt animal that wasn't theirs. Casts the visitor as a person who doesn't walk past. Donor-identity, not guilt.
Proof signature | 'Tobler's Ledger' | A living wall of every animal RKM kept its promise to, named; Tobler = #00 'Not a rescue. The reason.' Replaces vanity counters; turns smallness into intimacy. [NEEDS DATA: names/outcomes]
Art-direction light | 'The Long Night -> First Light' | Copper = lamp-light of the night vigil; sections move night->dawn (rescue->release). A lighting grade, not animation.
Why ownable | Derived from RKM's literal origin + ethos | Other NGOs lead with the animal's suffering; only RKM's origin is the human choice not to walk past. Impossible to copy.
Rejected (un-ownable) | Paw particles, rescue counters, scrolling timelines, animal cursors, mesh-gradient hero | Any NGO can do these; none make RKM memorable.
Typography | Editorial serif (e.g. Fraunces/Source Serif, self-hosted) + Inter workhorse + Noto Sans Devanagari | Serif carries the conscience (story/pull-quotes); Inter for UI/body. Modular scale; 60-66ch.
Colour roles | Ink text; Snow ground; Copper = lamp-light/large-accent only; Copper-dark for large copper text; Night #171411 for dark sections | All text pairings AA-verified; copper is light = never body text.
Photography | Real documentary, eye-level, available light, warm-neutral grade; dignity & hope, before/after | No stock, ever. Holding type frames where real photos absent. [NEEDS DATA: more cleared photos]
100-word jury pitch | See Master Operating Document / Experience Design | 'The charity you couldn't walk past — told through the names it kept, from the long night to first light.'

## 4. Experience Design
Area | Beat | What you see | Copy hierarchy | What unfolds | What you feel
Home F0 | Arrival | One real animal, eye-level, night lamp-light, still | 'Most people walk past.' / 'We're who they call when someone doesn't.' / CTA 'Don't walk past' | Line 2 settles a half-beat after line 1; animal holds gaze; no carousel | Pause / recognition (not guilt)
Home F1 | Founding truth | Editorial column; the vet-door memory | Pull-quote: 'They couldn't walk past it.' | Text reveals at reading pace; copper pull-quote | Confidence / trust forms
Home F2 | Honesty turn | Short candour statement | 'We'd rather grow slowly and keep every promise.' | Quiet | Respect
Home F3 | Four ways | Rescue / Feed / Heal / Shelter — eye-level photos | One line each (rescue/feed/heal/shelter) | Reveal one at a time | Clarity (what+how)
Home F4 | Tobler's Ledger (PEAK) | Wall of named animals; Tobler #00 | 'Not a rescue. The reason.' + outcomes Recovered/Adopted/Released/Resting | Names rise into focus; tap reveals one-line story; light warms to dawn | Awe / memory [NEEDS DATA]
Home F5 | The mirror | Turn to the visitor | 'You can't be everywhere. But you can be the reason someone doesn't walk past.' | Quiet pivot | Agency
Home F6 | The ask | Monthly-first donate + real testimonial + where-money-goes | 'You didn't walk past. Here's what that does.' | Calm form | Action feels easy & meaningful
Home F7 | Trust + close | Credentials, address, honest note | Real reg numbers; 'we keep our promises' | Settle | Confidence / memorable exit
Donate | Join, not checkout | Left: why (Tobler + testimonial). Right: form | Monthly = 'Stay with them'; button speaks identity | 2nd-lowest preselect; fee-cover; thank-you 'You're one of them now' | Chosen, staying, welcomed
Ledger | Destination | Names as texture; filter by outcome; tap = reverent card | 'Every animal we ever kept a promise to.' | Night->dawn as you read; your gift becomes a name you know | Reverence, intimacy, permanence
Mobile | Thumb & street | Animal fills screen; line in thumb-zone; UPI/GPay first | Same identity copy | Ledger as flickable register; big tap targets | Calm, fast, one-handed
Journey | First-time | cold -> hero stop -> story -> ledger belief -> mirror identity -> act/remember | - | - | Curiosity->trust->belief->identity->action/memory
Journey | Returning | Recognised; pitch skipped; 'Welcome back' | 'Give again' / 'Stay with them' | Shows outcome tied to last gift [NEEDS DATA] | Remembered, invited deeper
Journey | Monthly (Guardian) | Inside the circle; their named animal + updates | 'You don't walk past — every day.' | Belonging > asking; 'add another name' | Belonging, pride

## 5. Website Improvements
ID | Category | Research finding | Evidence | Why it matters | Recommended action | Implementation approach | Dependencies | Owner | Success metric | Status
RKMF-006 | SEO/Trust | schema.org tagged as US 501(c)(3) | layout.tsx | False statutory claim on Indian trust | Correct NGO schema | DONE - NGO + Indian IDs + DonateAction | - | Eng | Rich Results: valid NGO+DonateAction | DONE
RKMF-013 | Conversion | UPI/GPay grey text, not primary mobile | DonateWidget | UPI dominant India rail; mobile drop-off | UPI-first on mobile | Surface UPI/wallets above card | - | Eng | Mobile completion within 5% of desktop | OPEN
RKMF-020 | Storytelling | No story on homepage | HomeExperience | Emotion should precede the ask | Lead home with one animal | Signature hero (Concept 1) | 019 | Design | Homepage 5-sec test pass | OPEN
RKMF-021 | Perf/Privacy | Fonts from Google CDN | layout.tsx head | IP leak (DPDP) + render-block | Self-host fonts | vars or /public/fonts +@font-face | Build test | Eng | No Google font request; LCP/CLS | BUILD-BLOCKED
RKMF-022 | Perf | 0x next/image; 12 raw <img> | components | CLS + oversized mobile transfer | Migrate to next/image | srcset+dimensions+AVIF | Build test | Eng | Lighthouse images pass; CLS<=0.05 | OPEN
RKMF-026 | A11y/Motion | reduced-motion unverified (Lenis/GSAP) | components | Scroll-hijack nausea/AAA fail | Audit motion layer | Ensure off-switch; no LCP delay | - | Eng | Reduced-motion verified | OPEN
RKMF-027 | Hygiene | prototype/prototype-v2 dead routes | app/ | Ships stale/experimental routes | Delete or noindex | Remove from build | - | Eng | Dead routes removed/noindexed | OPEN
RKMF-043 | i18n | Hindi = parallel hardcode | /hi components | EN/HI translation drift risk | Shared content model | Single source for EN/HI | - | Eng | Zero EN/HI drift | OPEN
RKMF-049 | Audit | Shop flow unaudited | /shop | Separate conversion path | Audit shop funnel | Funnel + states review | - | Eng | Shop funnel audited | OPEN
RKMF-050 | Audit | Content/editorial SEO unaudited | - | Only technical SEO covered | Content/keyword plan | Blog + keyword strategy | - | Marketing | Organic growth tracked | OPEN

## 6. Fundraising Improvements
ID | Category | Research finding | Evidence | Why it matters | Recommended action | Implementation approach | Dependencies | Owner | Success metric | Status
RKMF-015 | Conversion | No donor segmentation | Flow | Cold form for all; misses upgrade/win-back | Segment first/return/lapsed | Returning->give-again; lapsed->win-back | 005 | Fundraising+Eng | Returning/lapsed conversion up | OPEN
RKMF-031 | Major gifts | No major-donor journey | - | Rs.25k-1L donors need high-touch | Build major-donor path | Stewardship + personal ask | Donor data | Fundraising | Journey defined + tracked | DATA-BLOCKED
RKMF-032 | CSR | CSR landing not audited for conversion | /csr | 12A/80G/CSR-1 unlock corporate giving | Rebuild CSR flow | Audit + converting landing | - | Fundraising | CSR landing conversion tracked | OPEN
RKMF-033 | CSR | No CSR case studies | - | Corporates need proof | Build case studies | One-pager + outreach assets | Cases | Founder+Fundraising | CSR case studies published | FACT-BLOCKED
RKMF-034 | Major gifts | No top-20 donor analysis | - | Unknown who/why top donors give | Segment + follow-up | Define donor journey | Donor data | Fundraising | Top-20 segmented + follow-up | DATA-BLOCKED
RKMF-035 | Retention | No new-donor nurture | - | Leaves second-gift money on table | Lifecycle series | thank-you->impact->monthly | 005 | Fundraising | Nurture live; second-gift up | OPEN
RKMF-036 | Retention | No lapsed win-back | - | Lapsed donors recoverable | Win-back flow | Email + WhatsApp | Donor data | Fundraising | Reactivation rate tracked | DATA-BLOCKED
RKMF-037 | Retention | No monthly impact email | - | Retention driver for monthly donors | Monthly impact email | Named-animal update | Impact #s | Fundraising | Monthly email live; retention up | FACT-BLOCKED
RKMF-038 | Retention | No WhatsApp journeys | opt-in exists unused | India-primary channel unused | WhatsApp journeys | Impact updates via opt-in | Provider | Eng+Fundraising | WhatsApp journey live | OPEN
RKMF-039 | Fundraising | No campaign calendar | - | Misses festival/emergency/seasonal lift | Annual calendar | Templates + cadence | - | Fundraising | Calendar published; campaign lift | OPEN
RKMF-040 | Recurring | Generic toggle, no program identity | DonateWidget | Programs beat generic monthly | Guardian/Sponsor/Feed | Named identity + updates | Named animals | Fundraising+Design | Programs live; recurring share up | OPEN
RKMF-041 | Funnel | No volunteer->donor path | - | Volunteers convert to monthly donors | Volunteer journey | Conversion path | - | Fundraising | Volunteer->donor tracked | OPEN
RKMF-042 | International | FCRA unconfirmed | No FCRA in code | Foreign giving is a legal gate | Confirm FCRA | Document basis before any claim | Legal | Founder | FCRA status documented | FACT-BLOCKED
RKMF-044 | Legacy | No gifts-in-wills | Benchmark | ~55% of RSPCA income; largest channel | Legacy page + enquiry | India-correct wording | Legal wording | Founder+Fundraising | Legacy page live; enquiries tracked | OPEN
RKMF-045 | Tribute | No memorial/in-honour giving | Benchmark | Occasion, high-emotion giving | Tribute donate path | Paper/e-card | E-card tmpl | Fundraising+Eng | Tribute gifts tracked | OPEN
RKMF-046 | Peer-to-peer | /fundraiser unaudited/unoptimised | app/fundraiser | Supporters raise on RKM's behalf | Optimise P2P | Shareable pages; birthday prompts | - | Fundraising+Eng | Funds raised via P2P | OPEN
RKMF-047 | Adoption | No adoptable-animals portal | Mission incl. adoption | Engagement->foster->donor funnel | Rehoming portal | Listings -> foster/adopt | Real animals | Founder+Eng | Foster/adopt leads tracked | FACT-BLOCKED
RKMF-048 | In-kind | No structured wishlist | Testimonial shows in-kind | Low-friction non-cash entry | Published wishlist | Food/blankets/meds list | Supply list | Founder+Fundraising | In-kind gifts tracked | OPEN

## 7. Donation Flow
ID | Category | Research finding | Evidence | Why it matters | Recommended action | Implementation approach | Dependencies | Owner | Success metric | Status
RKMF-001 | Conversion | Frequency defaulted to one-time | DonateWidget.tsx state init | Recurring donors worth multiples; biggest revenue lever | Default to monthly | DONE - default flipped; one-time one tap away | - | Eng/Conversion | Recurring share of gifts up vs baseline | DONE
RKMF-002 | Conversion | No fee-cover option | DonateWidget | Recovers ~2% gateway fee at ~zero cost | Optional cover-fee | DONE - checkbox + live recompute | - | Eng | Fee-cover opt-in rate tracked | DONE
RKMF-003 | Analytics | No funnel instrumentation | No analytics in repo | Conversion unmeasurable without it | Instrument funnel | DONE - lib/analytics.ts + events, consent-gated | - | Eng | All 5 funnel steps firing | DONE
RKMF-004 | Compliance | Cookie banner cosmetic - no reject, gates nothing | CookieBanner.tsx | DPDP/GDPR breach; blocks analytics go-live | Granular consent | Reject=accept; set consent flag only on opt-in | - | Eng+Founder | No analytics pre-consent (DevTools) | OPEN
RKMF-005 | Analytics | No provider deployed -> no baseline | Repo | All KPIs unmeasurable | Deploy cookieless analytics | Plausible/Fathom; connect track() | 004 | Eng | 28-day field baseline established | OPEN
RKMF-009 | Emotion/Trust | No story/proof at the ask | donate-now page | Emotion+proof at decision lifts completion | Story+testimonial at ask | DONE - Tobler + monthly-donor testimonial | - | Design | Form completion up (funnel) | DONE
RKMF-010 | Trust | No where-money-goes strip at ask | donate-now | Pre-empts #1 NGO objection | Allocation strip | Honest % beside widget | Fund % | Founder+Design | Completion up; overhead objection down | FACT-BLOCKED
RKMF-011 | Conversion | Same tiers monthly/one-time; no low entry | DonateWidget | Misframed monthly; sticker shock | 4-tier ladder | Monthly lower absolutes + annual impact | Cost math | Design+Eng | Avg gift & monthly take-rate up | FACT-BLOCKED
RKMF-013 | Conversion | UPI/GPay grey text, not primary mobile | DonateWidget | UPI dominant India rail; mobile drop-off | UPI-first on mobile | Surface UPI/wallets above card | - | Eng | Mobile completion within 5% of desktop | OPEN
RKMF-014 | Conversion | Rs.1000 floor vs peers' Rs.500 | DonateWidget/api | Excludes small/first-time gifts | Lower floor to Rs.500 | Add micro-impact line | Confirm cost | Eng/Conversion | First-time gift volume up | OPEN
RKMF-015 | Conversion | No donor segmentation | Flow | Cold form for all; misses upgrade/win-back | Segment first/return/lapsed | Returning->give-again; lapsed->win-back | 005 | Fundraising+Eng | Returning/lapsed conversion up | OPEN

## 8. Trust Layer
ID | Category | Research finding | Evidence | Why it matters | Recommended action | Implementation approach | Dependencies | Owner | Success metric | Status
RKMF-006 | SEO/Trust | schema.org tagged as US 501(c)(3) | layout.tsx | False statutory claim on Indian trust | Correct NGO schema | DONE - NGO + Indian IDs + DonateAction | - | Eng | Rich Results: valid NGO+DonateAction | DONE
RKMF-009 | Emotion/Trust | No story/proof at the ask | donate-now page | Emotion+proof at decision lifts completion | Story+testimonial at ask | DONE - Tobler + monthly-donor testimonial | - | Design | Form completion up (funnel) | DONE
RKMF-010 | Trust | No where-money-goes strip at ask | donate-now | Pre-empts #1 NGO objection | Allocation strip | Honest % beside widget | Fund % | Founder+Design | Completion up; overhead objection down | FACT-BLOCKED
RKMF-012 | Trust | Zero impact numbers on homepage | HomeExperience | No proof density; can't gauge impact | Proof stat band | Rescued/treated/fed, dated | Impact #s | Founder+Design | 5-sec test pass; trust uplift | FACT-BLOCKED
RKMF-016 | Trust | No financials/annual report/fund % | Site | Certs prove registration, not stewardship | Transparency section | Downloads + optional live dashboard | Docs | Founder | Transparency page live | FACT-BLOCKED
RKMF-017 | Trust | Founders/board anonymous | about page | A named face lifts trust | Named leadership | Photo+bio on /about | Consent | Founder | Leadership section live | FACT-BLOCKED
RKMF-018 | Trust | No third-party validation | Site | Self-published certs only | Validation strip | Partner vets/press/ratings | Data | Founder | Validation strip live | FACT-BLOCKED
RKMF-019 | Storytelling | One story; no named rescue/before-after | about/blog | Stories outperform every technical fix | 3-5 rescue narratives | Named, before/after, outcome | Stories+photos | Founder+Design | Stories live; story_viewed up | FACT-BLOCKED
Real credentials to surface (true, present):
Trust E-30560
PAN AACTR4271L
12A 47522
80G CITE80G9792014-152016-17
CSR-1 CSR00089305
DARPAN MH/2024/0457296

## 9. Content Requirements
Content item | Detail | Provider | Unblocks | Status
Mission one-liner | The single canonical sentence | Founder | Blocks hero/messaging | OPEN
Impact numbers + dates | Animals rescued/treated/sterilised/vaccinated/fed/rehomed | Founder | RKMF-012/037 | OPEN
Cost-per-outcome math | Real Rs. per meal/treatment/month | Founder | RKMF-010/011/014 | OPEN
Fund-allocation % | Where-the-money-goes split | Founder | RKMF-010/016 | OPEN
Named rescue stories | 3-5 animals: name, before/after, outcome | Founder | RKMF-019/040; Tobler's Ledger | OPEN
Animal names + outcomes (Ledger) | Every helped animal: name + Recovered/Adopted/Released/Resting | Founder | RKMF-047; signature concept | OPEN
Cleared photography | Documentary photos of real animals (rights cleared) | Founder | All concepts; RKMF-019 | PARTIAL
Board / leadership + consent | Names, roles, photos, consent | Founder | RKMF-017 | OPEN
Audited financials | For transparency section | Founder | RKMF-016 | OPEN
CSR case studies | Corporate proof | Founder | RKMF-033 | OPEN
Supply / wishlist | In-kind needs list | Founder | RKMF-048 | OPEN
FCRA status | Legal foreign-funding basis | Founder/Legal | RKMF-042 | OPEN
Active campaign | Any live match/challenge grant | Founder | §8 urgency | OPEN

## 10. Design Requirements
Area | Element | Spec | Notes
Typography | Display | Editorial serif (Fraunces/Source Serif), self-hosted | Conscience/story/pull-quotes
Typography | Workhorse | Inter (+ Noto Sans Devanagari for /hi) | UI, body, forms
Typography | System | Modular scale ~1.25; line length 60-66ch; one signature pull-quote treatment | Editorial craft
Colour | Ink #111111 | Primary text / night | AA/AAA on snow
Colour | Snow/Mist #F5F5F5 | Page ground / whitespace | -
Colour | Copper #B89245 | Lamp-light, large accents only | Not body text (light)
Colour | Copper-dark #8F6A2A | Copper-coloured text (large), links on snow | AA large only
Colour | Night #171411 | Concept-3 dark sections | White text = AA
Photography | Treatment | Real documentary, eye-level, available light, warm-neutral grade; before/after | No stock; holding type if absent
Grid | Layout | Baseline grid; editorial asymmetry; generous whitespace | Premium signal
Motion | Discipline | Restraint = signature; hero stays still; reduced-motion safe; no LCP delay | Concept integrity

## 11. Development Requirements
Domain | Item | Requirement | Status / ref
Security | CSP | Strict CSP: nonce script-src (no unsafe-inline/eval); frame-src=processor; object-src none; base-uri self | A+ securityheaders/Observatory
Security | Headers | HSTS preload, Referrer-Policy, Permissions-Policy, X-Content-Type-Options | Present; verify
Security | PCI | SAQ-A: card data never touches DOM/servers (Razorpay hosted) | Maintain
Security | Secrets/scanning | Rotate exposed secrets; gitleaks + Dependabot in CI | CI added
Performance | CWV | LCP<=2.5s, INP<=200ms, CLS<=0.1 at field p75; Lighthouse>=95 mobile | Lab + 28-day field
Performance | Budgets | JS<=150KB gz, CSS<=50KB, donate path<=500KB; CI-enforced | CI budgets
Performance | Images/Fonts | AVIF/WebP, srcset, dims; self-host fonts, font-display swap | RKMF-021/022
Analytics | Provider | Cookieless, IP-anon, consent-gated (Plausible/Fathom/server-side) | RKMF-004/005
Analytics | Funnel | view->frequency->amount->details->razorpay->success/failed->thankyou->upgrade | Built; deploy
SEO | Basics | Unique title/meta, canonical, sitemap+robots, one h1, alt text, OG/Twitter | Mostly present
SEO | Schema | NGO/NonprofitType, Organization, DonateAction JSON-LD | RKMF-006 DONE
SEO | i18n | lang per page, hreflang, lakh/crore formatting, translated transactional copy | EN/HI
Quality | Gates | Unit + donation E2E (Playwright); Lighthouse-CI + axe build-failing | RKMF-024; CI added
States | Resilience | Loading skeletons/empty/error states; custom 404; error boundary; idempotency | §14

## 12. Master Backlog
ID | Category | Research finding | Evidence | Why it matters | Recommended action | Implementation approach | Dependencies | Owner | Success metric | Status
RKMF-001 | Conversion | Frequency defaulted to one-time | DonateWidget.tsx state init | Recurring donors worth multiples; biggest revenue lever | Default to monthly | DONE - default flipped; one-time one tap away | - | Eng/Conversion | Recurring share of gifts up vs baseline | DONE
RKMF-002 | Conversion | No fee-cover option | DonateWidget | Recovers ~2% gateway fee at ~zero cost | Optional cover-fee | DONE - checkbox + live recompute | - | Eng | Fee-cover opt-in rate tracked | DONE
RKMF-003 | Analytics | No funnel instrumentation | No analytics in repo | Conversion unmeasurable without it | Instrument funnel | DONE - lib/analytics.ts + events, consent-gated | - | Eng | All 5 funnel steps firing | DONE
RKMF-004 | Compliance | Cookie banner cosmetic - no reject, gates nothing | CookieBanner.tsx | DPDP/GDPR breach; blocks analytics go-live | Granular consent | Reject=accept; set consent flag only on opt-in | - | Eng+Founder | No analytics pre-consent (DevTools) | OPEN
RKMF-005 | Analytics | No provider deployed -> no baseline | Repo | All KPIs unmeasurable | Deploy cookieless analytics | Plausible/Fathom; connect track() | 004 | Eng | 28-day field baseline established | OPEN
RKMF-006 | SEO/Trust | schema.org tagged as US 501(c)(3) | layout.tsx | False statutory claim on Indian trust | Correct NGO schema | DONE - NGO + Indian IDs + DonateAction | - | Eng | Rich Results: valid NGO+DonateAction | DONE
RKMF-007 | Security | CSP carried unsafe-eval | next.config.mjs | XSS attack surface on money/PII site | Remove unsafe-eval | DONE - removed; verify on preview | - | Eng | securityheaders A+; donate clean | DONE
RKMF-008 | Hygiene | 357 junk files committed | git ls-files | Pollutes audits; risks stale content | Purge + gitignore | IN-PR - cleanup+commit script (Mac) | - | Eng | git junk count = 0 | IN-PR
RKMF-009 | Emotion/Trust | No story/proof at the ask | donate-now page | Emotion+proof at decision lifts completion | Story+testimonial at ask | DONE - Tobler + monthly-donor testimonial | - | Design | Form completion up (funnel) | DONE
RKMF-010 | Trust | No where-money-goes strip at ask | donate-now | Pre-empts #1 NGO objection | Allocation strip | Honest % beside widget | Fund % | Founder+Design | Completion up; overhead objection down | FACT-BLOCKED
RKMF-011 | Conversion | Same tiers monthly/one-time; no low entry | DonateWidget | Misframed monthly; sticker shock | 4-tier ladder | Monthly lower absolutes + annual impact | Cost math | Design+Eng | Avg gift & monthly take-rate up | FACT-BLOCKED
RKMF-012 | Trust | Zero impact numbers on homepage | HomeExperience | No proof density; can't gauge impact | Proof stat band | Rescued/treated/fed, dated | Impact #s | Founder+Design | 5-sec test pass; trust uplift | FACT-BLOCKED
RKMF-013 | Conversion | UPI/GPay grey text, not primary mobile | DonateWidget | UPI dominant India rail; mobile drop-off | UPI-first on mobile | Surface UPI/wallets above card | - | Eng | Mobile completion within 5% of desktop | OPEN
RKMF-014 | Conversion | Rs.1000 floor vs peers' Rs.500 | DonateWidget/api | Excludes small/first-time gifts | Lower floor to Rs.500 | Add micro-impact line | Confirm cost | Eng/Conversion | First-time gift volume up | OPEN
RKMF-015 | Conversion | No donor segmentation | Flow | Cold form for all; misses upgrade/win-back | Segment first/return/lapsed | Returning->give-again; lapsed->win-back | 005 | Fundraising+Eng | Returning/lapsed conversion up | OPEN
RKMF-016 | Trust | No financials/annual report/fund % | Site | Certs prove registration, not stewardship | Transparency section | Downloads + optional live dashboard | Docs | Founder | Transparency page live | FACT-BLOCKED
RKMF-017 | Trust | Founders/board anonymous | about page | A named face lifts trust | Named leadership | Photo+bio on /about | Consent | Founder | Leadership section live | FACT-BLOCKED
RKMF-018 | Trust | No third-party validation | Site | Self-published certs only | Validation strip | Partner vets/press/ratings | Data | Founder | Validation strip live | FACT-BLOCKED
RKMF-019 | Storytelling | One story; no named rescue/before-after | about/blog | Stories outperform every technical fix | 3-5 rescue narratives | Named, before/after, outcome | Stories+photos | Founder+Design | Stories live; story_viewed up | FACT-BLOCKED
RKMF-020 | Storytelling | No story on homepage | HomeExperience | Emotion should precede the ask | Lead home with one animal | Signature hero (Concept 1) | 019 | Design | Homepage 5-sec test pass | OPEN
RKMF-021 | Perf/Privacy | Fonts from Google CDN | layout.tsx head | IP leak (DPDP) + render-block | Self-host fonts | vars or /public/fonts +@font-face | Build test | Eng | No Google font request; LCP/CLS | BUILD-BLOCKED
RKMF-022 | Perf | 0x next/image; 12 raw <img> | components | CLS + oversized mobile transfer | Migrate to next/image | srcset+dimensions+AVIF | Build test | Eng | Lighthouse images pass; CLS<=0.05 | OPEN
RKMF-023 | Security | CSP script-src unsafe-inline | next.config | Weakens XSS protection | Nonce CSP | Per-request nonce via middleware | Deploy test | Eng | CSP no unsafe-inline; A+ | OPEN
RKMF-024 | Quality | No donation E2E | Repo | Revenue path untested | Playwright E2E | incl declined/idempotent/3DS | - | Eng | E2E green in CI | OPEN
RKMF-025 | Accessibility | No manual WCAG 2.2 AA pass | - | Lighthouse audits a minority of criteria | Manual a11y passes | keyboard/SR/zoom/target/focus | - | Eng | Documented AA pass | OPEN
RKMF-026 | A11y/Motion | reduced-motion unverified (Lenis/GSAP) | components | Scroll-hijack nausea/AAA fail | Audit motion layer | Ensure off-switch; no LCP delay | - | Eng | Reduced-motion verified | OPEN
RKMF-027 | Hygiene | prototype/prototype-v2 dead routes | app/ | Ships stale/experimental routes | Delete or noindex | Remove from build | - | Eng | Dead routes removed/noindexed | OPEN
RKMF-028 | Architecture | DB schema not version-controlled | No migrations | Codebase not full source of truth; DR risk | Commit migrations | SQL migrations in repo | - | Eng | Schema reproducible from repo | OPEN
RKMF-029 | Security | Admin = single static token | adminAuth.ts | No per-user accountability | Per-user auth | Supabase Auth | - | Eng | Per-user admin auth live | OPEN
RKMF-030 | Security | Live secrets exposed in chat | Handover | Worst-case PII/payment incident | Rotate secrets | Supabase/Resend/admin/webhook | - | Founder | All exposed secrets rotated | FOUNDER
RKMF-031 | Major gifts | No major-donor journey | - | Rs.25k-1L donors need high-touch | Build major-donor path | Stewardship + personal ask | Donor data | Fundraising | Journey defined + tracked | DATA-BLOCKED
RKMF-032 | CSR | CSR landing not audited for conversion | /csr | 12A/80G/CSR-1 unlock corporate giving | Rebuild CSR flow | Audit + converting landing | - | Fundraising | CSR landing conversion tracked | OPEN
RKMF-033 | CSR | No CSR case studies | - | Corporates need proof | Build case studies | One-pager + outreach assets | Cases | Founder+Fundraising | CSR case studies published | FACT-BLOCKED
RKMF-034 | Major gifts | No top-20 donor analysis | - | Unknown who/why top donors give | Segment + follow-up | Define donor journey | Donor data | Fundraising | Top-20 segmented + follow-up | DATA-BLOCKED
RKMF-035 | Retention | No new-donor nurture | - | Leaves second-gift money on table | Lifecycle series | thank-you->impact->monthly | 005 | Fundraising | Nurture live; second-gift up | OPEN
RKMF-036 | Retention | No lapsed win-back | - | Lapsed donors recoverable | Win-back flow | Email + WhatsApp | Donor data | Fundraising | Reactivation rate tracked | DATA-BLOCKED
RKMF-037 | Retention | No monthly impact email | - | Retention driver for monthly donors | Monthly impact email | Named-animal update | Impact #s | Fundraising | Monthly email live; retention up | FACT-BLOCKED
RKMF-038 | Retention | No WhatsApp journeys | opt-in exists unused | India-primary channel unused | WhatsApp journeys | Impact updates via opt-in | Provider | Eng+Fundraising | WhatsApp journey live | OPEN
RKMF-039 | Fundraising | No campaign calendar | - | Misses festival/emergency/seasonal lift | Annual calendar | Templates + cadence | - | Fundraising | Calendar published; campaign lift | OPEN
RKMF-040 | Recurring | Generic toggle, no program identity | DonateWidget | Programs beat generic monthly | Guardian/Sponsor/Feed | Named identity + updates | Named animals | Fundraising+Design | Programs live; recurring share up | OPEN
RKMF-041 | Funnel | No volunteer->donor path | - | Volunteers convert to monthly donors | Volunteer journey | Conversion path | - | Fundraising | Volunteer->donor tracked | OPEN
RKMF-042 | International | FCRA unconfirmed | No FCRA in code | Foreign giving is a legal gate | Confirm FCRA | Document basis before any claim | Legal | Founder | FCRA status documented | FACT-BLOCKED
RKMF-043 | i18n | Hindi = parallel hardcode | /hi components | EN/HI translation drift risk | Shared content model | Single source for EN/HI | - | Eng | Zero EN/HI drift | OPEN
RKMF-044 | Legacy | No gifts-in-wills | Benchmark | ~55% of RSPCA income; largest channel | Legacy page + enquiry | India-correct wording | Legal wording | Founder+Fundraising | Legacy page live; enquiries tracked | OPEN
RKMF-045 | Tribute | No memorial/in-honour giving | Benchmark | Occasion, high-emotion giving | Tribute donate path | Paper/e-card | E-card tmpl | Fundraising+Eng | Tribute gifts tracked | OPEN
RKMF-046 | Peer-to-peer | /fundraiser unaudited/unoptimised | app/fundraiser | Supporters raise on RKM's behalf | Optimise P2P | Shareable pages; birthday prompts | - | Fundraising+Eng | Funds raised via P2P | OPEN
RKMF-047 | Adoption | No adoptable-animals portal | Mission incl. adoption | Engagement->foster->donor funnel | Rehoming portal | Listings -> foster/adopt | Real animals | Founder+Eng | Foster/adopt leads tracked | FACT-BLOCKED
RKMF-048 | In-kind | No structured wishlist | Testimonial shows in-kind | Low-friction non-cash entry | Published wishlist | Food/blankets/meds list | Supply list | Founder+Fundraising | In-kind gifts tracked | OPEN
RKMF-049 | Audit | Shop flow unaudited | /shop | Separate conversion path | Audit shop funnel | Funnel + states review | - | Eng | Shop funnel audited | OPEN
RKMF-050 | Audit | Content/editorial SEO unaudited | - | Only technical SEO covered | Content/keyword plan | Blog + keyword strategy | - | Marketing | Organic growth tracked | OPEN
RKMF-051 | Audit | Real-device/field perf unmeasured | - | Lab != field; CWV need p75 | Real-device + field test | CrUX/RUM p75 | 005+devices | Eng | Field p75 meets target | DATA-BLOCKED
RKMF-052 | Audit | Email deliverability unverified | Relied on handover | Silent email failure risk | Deliverability review | Inbox placement test | - | Eng | Deliverability verified | OPEN

## 13. Batch Plan
Batch | Goal | Issues | Expected outcome | Dependencies
Batch 1 | Critical revenue/trust/compliance; turn on measurement | 001-010 | Monthly-first live; analytics measuring; compliant consent; trust at ask | 005 needs 004; 010 needs fund %
Batch 2 | Lift completion + avg gift; close trust/proof | 011-020 | 4-tier ladder, UPI-first, proof density, named stories, segmentation | Mostly fact-blocked
Batch 3 | World-class technical bar | 021-030 | Self-host fonts, next/image, nonce CSP, E2E, manual a11y, migrations, secret rotation | Build/deploy test
Batch 4 | Open high-value channels | 031-034 | Major-donor journey + CSR conversion + case studies | Donor data + cases
Batch 5 | Retention engine | 035-038 | Nurture, win-back, monthly impact, WhatsApp | Analytics + impact #s
Batch 6 | Recurring + new channels | 039-048 | Guardian/Sponsor/Feed, legacy, tribute, P2P, adoption, wishlist, calendar | Named animals, legal, content
Carry-forward | Close audit surface | 049-052 | Shop, content SEO, field perf, deliverability | 051 needs analytics

## 14. Launch Checklist
Area | Item | Owner | Status
Payments | Add live Razorpay keys + live webhook secret | Founder | OPEN
Payments | One real test-card donation; confirm both emails + PDF arrive | Founder | OPEN
Infra | DNS cutover (A+CNAME) to Vercel; SSL auto-issues | Founder | OPEN
Security | Rotate all secrets exposed in chat | Founder | OPEN
Security | CSP verified on preview (no console violations on donate) | Eng | OPEN
Compliance | Cookie consent live (reject=accept); analytics only post-consent | Eng | OPEN
Analytics | Provider live; funnel events confirmed | Eng | OPEN
Data | Reset demo/test data before launch | Founder | OPEN
Compliance | CA confirms 80G receipt format/wording | Founder | OPEN
Quality | CI green: build, Lighthouse-CI, axe, E2E, gitleaks | Eng | OPEN
Hygiene | Junk purge committed; dead prototype routes removed | Eng | IN-PR
A11y | Keyboard-only + SR pass on donate path | Eng | OPEN
Perf | Lab LCP/CLS targets met on donate path | Eng | OPEN
Content | Every published impact number sourced & true | Founder | OPEN

## 15. Award Submission Checklist
Area | Requirement | Status
Signature | One §6b concept implemented ('Didn't Walk Past' + Tobler's Ledger) | OPEN
Craft | §6a standards across all pages (type/photo/colour/grid) | OPEN
Clarity | 5-second test passes on every page (heuristic or user) | OPEN
Donation | Flow completes in <=3 steps on mid-range Android | OPEN
Trust | Every impact number sourced (§9); real photography only | OPEN
Performance | CWV field p75 good + Lighthouse>=95 mobile | OPEN
Accessibility | WCAG 2.2 AA manual pass (keyboard, SR, zoom, target size, focus) | OPEN
Compliance | Strict CSP A+; DPDP/GDPR consent; PCI SAQ-A | OPEN
Cross-browser | Latest Chrome/Safari/Firefox/Edge; 320px-1440px | OPEN
Motion | prefers-reduced-motion respected; no LCP delay | OPEN
Pitch | 100-word jury pitch is compelling & RKM-specific | DONE (drafted)
Memorability | Jury-memory + donor-memory test passes (identity + a name) | OPEN